## Table 1
Knowledge Areas | Project Management Process Groups
| Initiating | Planning | Executing | Monitoring & Controlling | Closing
| 4.1 Develop | 4.2 Develop Project | 4.3 Direct & | 5 Monitor & | 4.7 Close
4. Project Integration Management | Project Charter | Management Plan | Manage Project Work 4.4 Manage Project | Control Project Work 4.6 Perform Integrated | Project
|  |  | Knowledge | Change Control
|  | 5.1 Plan Scope |  | 5.5 Validate
|  | Management |  | Scope
5. Project Scope |  | 5.2 Collect |  | 5.6 Control
Management |  | Requirements |  | Scope
5.3 Define Scope
5.4 Create WBS
|  | 6.1 Plan Schedule |  | 6.6 Control
|  | Management |  | Schedule
6. Project Schedule Management |  | 6.2 Define Activities 6.3 Sequence Activities 6.4 Estimate Activity
Durations
6.5 Develop Schedule
|  | 7.1 Plan Cost |  | 7.4 Control Costs
7. Project Cost |  | Management
Management |  | 7.2 Estimate Costs
7.3 Determine Budget
8. Project Quality Management |  | 8.1 Plan Quality Management | 8.2 Manage Quality | 8.3 Control Quality
9. Project Resource Management |  | 9.1 Plan Resource Management 9.2 Estimate Activity Resources | 9.3 Acquire Resources 9.4 Develop Team 9.5 Manage Team | 9.6 Control Resources
10. Project Communications Management |  | 10.1 Plan Communications Management | 10.2 Manage Communications | 10.3 Monitor Communications
|  | 11.1 Plan Risk | 11.6 Implement | 11.7 Monitor
|  | Management | Risk Responses | Risks
11.2 Identify Risks
11.3 Perform
11. Project Risk Management |  | Qualitative Risk Analysis 11.4 Perform
Quantitative Risk
Analysis
11.5 Plan Risk
Responses
12. Project Procurement Management |  | 12.1 Plan Procurement Management | 12.2 Conduct Procurements | 12.3 Control Procurements
13. Project Stakeholder Management | 13.1 Identify Stakeholders | 13.2 Plan Stakeholder Engagement | 13.3 Manage Stakeholder Engagement | 13.4 Monitor Stakeholder Engagement

## Hoja1
Knowledge Areas | Project Management Process Groups
| Initiating | Planning | Executing | Monitoring & Controlling | Closing
4. Project Integration Management | 4.1 Develop Project Charter | 4.2 Develop Project Management Plan | 4.3 Direct & Manage Project Work | 5 Monitor & Control Project Work | 4.7 Close Project
|  |  | 4.4 Manage Project Knowledge | 4.6 Perform Integrated Change Control
5. Project Scope Management |  | 5.1 Plan Scope Management |  | 5.5 Validate Scope
|  | 5.2 Collect Requirements |  | 5.6 Control Scope
|  | 5.3 Define Scope |  | 5.6 Control Scope
5.4 Create WBS
6. Project Schedule Management |  | 6.1 Plan Schedule Management |  | 6.6 Control Schedule
6.2 Define Activities
6.3 Sequence Activities
6.4 Estimate Activity Durations
6.5 Develop Schedule
7. Project Cost Management |  | 7.1 Plan Cost Management |  | 7.4 Control Costs
7.2 Estimate Costs
7.3 Determine Budget
8. Project Quality Management |  | 8.1 Plan Quality Management | 8.2 Manage Quality | 8.3 Control Quality
9. Project Resource Management |  | 9.1 Plan Resource Management | 9.3 Acquire Resources | 9.6 Control Resources
|  | 9.2 Estimate Activity Resources | 9.4 Develop Team
9.5 Manage Team
10. Project Communications Management |  | 10.1 Plan Communications Management | 10.2 Manage Communications | 10.3 Monitor Communications
11. Project Risk Management |  | 11.1 Plan Risk Management | 11.6 Implement Risk Responses | 11.7 Monitor Risks
11.2 Identify Risks
11.3 Perform Qualitative Risk Analysis
11.4 Perform Quantitative Risk Analysis
11.5 Plan Risk Responses
12. Project Procurement Management |  | 12.1 Plan Procurement Management | 12.2 Conduct Procurements | 12.3 Control Procurements
13. Project Stakeholder Management | 13.1 Identify Stakeholders | 13.2 Plan Stakeholder Engagement | 13.3 Manage Stakeholder Engagement | 13.4 Monitor Stakeholder Engagement